## Summary
Tier 1 Alpha Test — Summary
Total test cases | 82
Bug-hunt tests (specifically probing known-risky permission behavior) | 7
Tests by section
A. Authentication & Account | 5
B. Org Onboarding (Super Admin) | 5
C. Org Settings | 6
D. Department Management | 8
E. Central Repository | 4
F. Document Detail Page | 10
G. Projects & Topics | 11
H. Org AI Assistant | 7
I. Needs Review Queue | 5
J. SharePoint Integration | 6
K. Billing & Subscription | 4
L. Dashboard & Knowledge Health | 4
M. Audit Log & Security | 2
N. Invite Acceptance | 3
O. Permission Boundary Sweep | 2
Tests by assignee
Johurul | 14
Tanzeela | 30
Sandeep | 19
Simran | 19

## All Tests
Test ID | Section | Test Title | Assigned To | Pair With | Role / Persona Required | Preconditions | Steps | Expected Result | Tag | Status (Pass/Fail/Blocked) | Bug Description / Notes | Severity (Low/Med/High/Critical) | Date Tested
T1 | A. Authentication & Account | Sign up with a new email | Johurul |  | New user | Use an email not already registered. | 1. Go to the Sign Up page. 2. Enter email + password, and try submitting WITHOUT checking the Terms & Conditions box (should be blocked). 3. Check the Terms & Conditions box and submit. | Blocked with a clear message when T&Cs unchecked. On valid submit, you're routed to the Verify OTP screen.
T2 | A. Authentication & Account | Verify OTP + resend cooldown | Johurul |  | New user | Just completed sign up. | 1. On the Verify OTP screen, enter an incorrect 6-digit code and submit. 2. Click 'Resend OTP' and confirm it goes into a ~30s cooldown (disabled/counting down). 3. Check email/inbox for the real code, enter it, submit. | Wrong code shows an inline error. Resend is rate-limited. Correct code verifies the account and routes to Sign In.
T3 | A. Authentication & Account | Sign in (valid + invalid credentials) | Johurul |  | Any registered user | Account already verified. | 1. Try signing in with a wrong password — confirm an inline error appears, not a crash. 2. Sign in with correct credentials. | Wrong password is rejected gracefully. Correct login lands on Welcome Back / org home.
T4 | A. Authentication & Account | Forgot password → reset password flow | Johurul |  | Any registered user |  | 1. From Sign In, click 'Forgot password?' and submit your email. 2. Note the message is generic either way (doesn't reveal whether the email exists). 3. On the Reset Password screen, enter the OTP from email + a new password + confirm password (try mismatched confirm first to check validation). 4. Submit with matching passwords. | Generic 'if this email exists...' message shown. Mismatched confirm is blocked client-side. Valid reset redirects to Sign In, and you can log in with the new password.
T5 | A. Authentication & Account | Change password while logged in + sign out | Johurul |  | Any logged-in user |  | 1. Go to Settings → Change Password. 2. Change your password (enter current + new). 3. Sign out. 4. Sign back in with the NEW password to confirm it actually took effect. | Password change succeeds and old password no longer works; new password does. Sign out clears the session and returns you to Sign In.
T6 | B. Org Onboarding (Super Admin) | Create a new organization | Tanzeela |  | New user (becomes Super Admin) | Fresh account with no org membership yet. | 1. Sign up / sign in with a brand-new account. 2. You should land on the 'Create organization' onboarding screen — enter an org name and submit. | Organization is created and you're taken straight into the Billing step of onboarding. Your role in this org is Super Admin.
T7 | B. Org Onboarding (Super Admin) | Onboarding — subscribe to a plan | Tanzeela |  | Super Admin, onboarding | Just created the org. | 1. On the Billing onboarding step, toggle Monthly/Yearly and review plan cards. 2. Subscribe to a plan. | Redirects to Stripe Checkout; after completing payment you land back in the app on the API Key onboarding step.
T8 | B. Org Onboarding (Super Admin) | Onboarding — OpenAI API key setup | Tanzeela |  | Super Admin, onboarding | Subscription active. | 1. Enter an obviously invalid key and click 'Verify Key' — confirm it's rejected with an error. 2. Enter a real, valid OpenAI key and click 'Verify Key'. 3. Once verified, click 'Save & Continue'. | Invalid key is rejected with a clear message and 'Save & Continue' stays hidden until verified. Valid key saves and advances to the Celebrate screen.
T9 | B. Org Onboarding (Super Admin) | Celebrate screen is one-time only | Tanzeela |  | Super Admin | Just finished the API key step. | 1. Confirm the celebration/completion screen appears and click 'Go to home page'. 2. Manually navigate back to the onboarding celebrate URL for the same org. | First visit shows the celebration and marks onboarding complete. Revisiting the URL afterward redirects straight to the org home instead of re-showing it.
T10 | B. Org Onboarding (Super Admin) | Welcome Back screen / org switching | Tanzeela |  | User in one or more orgs | Belongs to at least one org. | 1. Sign in and observe the 'Welcome Back' screen. 2. If you belong to more than one org, switch between them. | Welcome Back lists your org(s) and lets you enter one; the app remembers your last-active org on next login.
T11 | C. Org Settings | Rename the organization | Tanzeela |  | Super Admin |  | 1. Go to Settings → General tab. 2. Change the organization name and Save. | Name updates and is reflected across the app (sidebar/header).
T12 | C. Org Settings | Invite members with each role (dept_admin / employee / guest) | Tanzeela |  | Super Admin |  | 1. Settings → Members tab → Invite Member. 2. Choose role 'Department Admin' — confirm you CANNOT submit until you also pick at least one department. 3. Send invites for one dept_admin, one employee, and one guest (use real test emails for your 3 teammates). | Role dropdown only offers Department Admin / Employee / Guest (not Super Admin). Dept-admin invite is blocked until a department is chosen. Invited users receive an invite link/email. | Setup
T13 | C. Org Settings | Reassign a Department Admin's departments | Tanzeela |  | Super Admin | At least one dept_admin exists (e.g. Sandeep) and 2+ departments exist. | 1. Settings → Members tab, find the dept_admin row, click 'Manage departments'. 2. Toggle which departments they administer, Save. | Checklist reflects current department assignments and saving updates them (verify by having that dept_admin test access to the added/removed department).
T14 | C. Org Settings | Department CRUD from Settings | Tanzeela |  | Super Admin |  | 1. Settings → Departments tab → create a new department. 2. Rename it using the pencil icon. 3. Delete it using the trash icon — if a confirmation about existing content appears, confirm twice as prompted. | Create/rename/delete all work only for Super Admin (pencil/trash icons should not appear for dept_admin or employee viewing the same tab). Delete asks for confirmation, especially if the department has documents/projects.
T15 | C. Org Settings | OpenAI API key management | Tanzeela |  | Super Admin |  | 1. Settings → API Key tab. 2. Replace the existing key with a new valid one, Save. 3. Clear the field and Save to remove the key entirely. | Key can be set, replaced, and removed. 'Configured' badge reflects current state. (Cross-check: after removing the key, org-level AI Chat should show the 'no API key configured' message — see Test on org chat.)
T16 | C. Org Settings | Integrations tab overview | Tanzeela |  | Super Admin |  | 1. Settings → Integrations tab. | Shows SharePoint (and any other connectors) with connection status, site count, and last sync date; 'Manage' navigates to the connector's own page.
T17 | D. Department Management | Open a department and confirm its 4 tabs | Sandeep |  | Dept Admin (admin of this department) |  | 1. Open a department you administer. 2. Confirm Documents / Projects / Members / Timeline tabs all load. | All 4 tabs render without errors.
T18 | D. Department Management | Upload documents scoped to a department | Sandeep |  | Dept Admin |  | 1. Documents tab → Upload Document. 2. Drag-and-drop (or browse) 2-3 files of mixed types (.pdf/.docx/.xlsx/.csv/.txt), try exceeding 10 files or an unsupported type to confirm it's rejected. 3. Pick a required Document Type category, submit. | Only accepted file types/count are allowed; clear error otherwise. Upload succeeds and documents appear (possibly first in Needs Review, depending on classification).
T19 | D. Department Management | Filter documents in the department view | Sandeep |  | Dept Admin | Department has several documents with different categories/types/lifecycle states. | 1. Apply Category, File Type, Lifecycle, and Date-range filters one at a time and in combination. | Each filter narrows results correctly; clearing filters restores the full list.
T20 | D. Department Management | Lifecycle transitions — allowed vs. blocked for Dept Admin | Sandeep |  | Dept Admin | Have one document you administer, and (if possible) one document in a department you do NOT administer. | 1. On a document in a department you ADMINISTER: change draft → published, then published → archived. Confirm both succeed. 2. Try published → retired or archived → anything: confirm the option is not offered / is rejected (Super Admin only). 3. If you have access to a document in a department you do NOT administer, try any lifecycle change there too. | Dept Admin can publish and archive only within departments they administer; retiring/un-archiving/reverting to draft is Super-Admin-only; attempting a transition in a department you don't administer is rejected.
T21 | D. Department Management | Classification, duplicate, and lifecycle-suggestion banners | Sandeep |  | Dept Admin | A document flagged 'needs review' with a suggested category/department, and/or a possible-duplicate flag. | 1. Open the classification review panel on a flagged document, adjust the suggested category/department, accept it. 2. On a document with a duplicate-signal banner, click Confirm, then on another try Dismiss. 3. On a document with a lifecycle-suggestion banner, dismiss it. | Accepting classification updates the doc's category/department. Confirming a duplicate flag marks it; dismissing clears the banner. Lifecycle-suggestion banner dismiss removes it without changing lifecycle.
T22 | D. Department Management | Project CRUD within a department | Sandeep |  | Dept Admin |  | 1. Projects tab → New Project (name + description). 2. Hover a project card → Edit (pencil) → change name/description, Save. 3. Hover → Delete (trash) → confirm. | Create/edit/delete all succeed for the department's admin.
T23 | D. Department Management | Department member management + bulk add-members modal | Sandeep |  | Dept Admin |  | 1. Members tab → Add member by email with role Member or Admin. 2. Remove a member (trash/X icon), confirm the prompt. 3. Create a brand-new department as Super Admin (or watch Tanzeela do it) and confirm the 'Add Members' bulk modal auto-opens right after creation, letting you multi-select org members with per-row role. | Add/remove work and reflect immediately in the list. New-department bulk-add modal appears automatically once, with working multi-select + per-row role.
T24 | D. Department Management | Department Timeline tab | Sandeep |  | Dept Admin | Department has some documents with extracted decisions. | 1. Open the Timeline tab. | Read-only, dated list of decision events with rationale and a link back to the source document.
T25 | E. Central Repository | Browse and filter the repository | Simran |  | Employee |  | 1. Open Repository. Apply Department, Category, File Type, Lifecycle, and Date filters, individually and combined. 2. Try pagination (Previous/Next). | Filters and pagination work; result count updates correctly; empty-filter combos show a clean empty state.
T26 | E. Central Repository | Upload + Open/Preview/Download from Repository | Simran |  | Employee |  | 1. Upload Document from the Repository page (choose a department, or 'Org-wide document'). 2. On an existing PDF, use Preview (should open inline) and Download. 3. On any document, use 'Open' (new tab) and 'View Details' (goes to the document page). | Upload succeeds; preview/download/open/view-details all work for accessible documents.
T27 | E. Central Repository | Guest role — read-only repository access | Johurul |  | Guest |  | 1. Open Repository as a Guest. 2. Confirm there is NO 'Upload Document' button. 3. Confirm you can still browse/open/download documents you have access to. | Guest cannot upload but retains read access to documents shared with them.
T28 | E. Central Repository | Employee cannot change document lifecycle | Simran |  | Employee |  | 1. On any repository document card, look for a 'Change status…' lifecycle control. | No lifecycle-change control is available to a plain employee (dept_admin/super_admin only).
T29 | F. Document Detail Page | Preview rendering across file types | Simran |  | Employee (owner or with access) | Have access to at least one PDF, DOCX, XLSX/CSV, and TXT document. | 1. Open each file type's document page and confirm the preview renders (PDF viewer w/ pages, DOCX text, spreadsheet with sheet/column breakdown, plain text). | Each format renders without errors or a broken viewer.
T30 | F. Document Detail Page | Chat with a document you own | Simran |  | Employee (document owner) | Own at least one uploaded document. | 1. Open the Chat tab, ask a question about the document's content. 2. While it's answering, click the cancel/stop icon. 3. Ask again, let it finish, then use Copy / Print / Expand on the message. 4. Use the trash icon to Clear Chat, confirm the dialog. | Answer is relevant and (where applicable) cites sources. Cancel stops the in-flight response. Copy/print/expand controls work. Clear Chat empties the conversation after confirming.
T31 | F. Document Detail Page | Summary tab — generate, regenerate, copy, print | Simran |  | Employee (document owner) |  | 1. Open Summary tab on an owned document. 2. Click Regenerate Summary (or Generate if none exists), wait for completion. 3. Copy the summary text and Print it. | Summary (re)generates successfully, button disables while processing, copy/print both work.
T32 | F. Document Detail Page | Pagewise Summary reading guide | Simran |  | Employee (document owner) | A multi-page document. | 1. Open the Pagewise Summary tab and page/scroll through the document. 2. Expand/collapse a couple of page cards. | Key points and reflection questions generate per page as you progress; progress indicator advances; expand/collapse works.
T33 | F. Document Detail Page | Fullscreen viewer with zoom | Simran |  | Employee |  | 1. Click Fullscreen on a PDF/TXT/DOCX document. 2. Zoom in, zoom out, and reset. | Fullscreen modal opens correctly and zoom controls behave as expected.
T34 | F. Document Detail Page | Star a document and filter by it | Simran |  | Employee (document owner) |  | 1. Star one of your own documents. 2. Go to its Project page (or wherever a Starred filter exists) and confirm it's included. | Starring persists and the Starred filter correctly includes it.
T35 | F. Document Detail Page | Rename and delete your own document | Simran |  | Employee (document owner) | Use a disposable test upload, not a document others depend on. | 1. Rename the document. 2. Delete it and confirm the confirmation dialog appears before it's removed. | Rename updates the filename everywhere it's shown. Delete requires confirmation and actually removes it.
T36 | F. Document Detail Page | Suggested project link — confirm/dismiss | Simran |  | Employee (document owner or admin) | A document with a suggested project link. | 1. Click Confirm on a suggested project link. 2. On another, click Dismiss. | Confirm attaches the document to that project; Dismiss removes the suggestion without linking.
T37 | F. Document Detail Page | [Bug-hunt] Admin viewing a colleague's document — do owner-only actions actually work? | Tanzeela |  | Super Admin, viewing a document owned by someone else | Open a document uploaded by Sandeep or Simran (not you), while logged in as Super Admin. | 1. Try: Regenerate Summary, Ask a question in Chat, Clear Chat, Star, Rename, Delete. 2. For each, note whether it visibly works, silently does nothing, or shows an error. | Record actual behavior for each action — the buttons appear enabled/active regardless of ownership, so this is specifically checking whether that's misleading. Report anything that looks 'broken' (button clickable but nothing happens, no error shown) as a bug. | Bug-hunt
T38 | F. Document Detail Page | [Bug-hunt] Dept Admin viewing a colleague's document in their own department | Sandeep |  | Dept Admin, viewing a document owned by someone else in a department they administer | Open a teammate's document in a department you administer. | 1. Try the same set of actions: Regenerate Summary, Ask, Clear Chat, Star, Rename, Delete. 2. Note pass/fail/silent-fail for each. | Same as above — document and report actual behavior, especially anything that looks clickable but does nothing. | Bug-hunt
T39 | G. Projects & Topics | Project CRUD from the Projects list | Sandeep |  | Dept Admin |  | 1. Projects page → search/filter by name. 2. Create a new project (choose department). 3. Edit an existing project's name/description. 4. Delete a project you created, confirm the dialog. | Search filters client-side instantly; create/edit/delete all succeed.
T40 | G. Projects & Topics | [Bug-hunt] Can an Employee or Guest create/edit/delete a project via the Projects list? | Simran |  | Employee | The Projects list page shows New Project / Edit / Delete controls to everyone who can reach it, with no visible role restriction in the UI. | 1. As Employee, try creating a new project. 2. Try editing and deleting a project you do NOT own (created by someone else). | Note whether this succeeds or is blocked. This is specifically testing whether the lack of a visible restriction means there's also no restriction on the server — report actual outcome either way. | Bug-hunt
T41 | G. Projects & Topics | Upload documents into a project | Sandeep |  | Dept Admin |  | 1. Open a project → Upload. 2. Upload a file, set category and Private/Public visibility. 3. Re-upload a file with the exact same name to confirm duplicate-filename detection. | Upload succeeds with required fields; re-uploading the same filename surfaces a clear duplicate-filename error inline.
T42 | G. Projects & Topics | Topic clustering view | Sandeep |  | Dept Admin | A project with several documents, some auto-clustered into topics. | 1. Open a project and review the Topic groups plus the always-present 'Unassigned' group. 2. Toggle grid/list view and try the search box and Starred/Unselected filter chips. | Documents are grouped sensibly by topic; view toggle, search, and filter chips all work.
T43 | G. Projects & Topics | Drag-and-drop a document between topics | Sandeep |  | Dept Admin (or document owner) |  | 1. Drag a document row by its grip handle onto a different Topic header. 2. Drag a document onto 'Unassigned' to unassign it. | Document moves to the target topic (or becomes unassigned) and the UI updates without a full reload.
T44 | G. Projects & Topics | Rename and delete a topic | Sandeep |  | Dept Admin |  | 1. Click the pencil icon on a topic header, rename it inline. 2. Click the trash icon on a topic header, confirm the browser confirm dialog. | Rename and delete both succeed.
T45 | G. Projects & Topics | [Bug-hunt] Can any org member rename/delete a topic in someone else's project? | Simran |  | Employee, not part of the project's department | Find a project in a department you are NOT a member of. | 1. Try renaming a topic in that project. 2. Try deleting a topic in that project. | Note whether this is blocked or allowed — topic rename/delete may only require being *some* org member rather than being scoped to that project/department. Report the actual outcome. | Bug-hunt
T46 | G. Projects & Topics | Auto-organize / Recluster — as project owner vs. non-owner admin | Sandeep | Tanzeela | Dept Admin | A project you personally created/own, with unassigned documents. | 1. As the project owner, click 'Auto-organize' (Sparkles icon) on the Unassigned group and confirm it clusters documents into topics. 2. Now have Tanzeela (Super Admin, NOT the project owner) open the same project and try 'Auto-organize' too. | Works for the owner. For Tanzeela: note whether it works, fails silently, or shows an error — recluster may be restricted to the literal project owner even for Super Admin. | Bug-hunt
T47 | G. Projects & Topics | Project Chat — ask AI, restricted to selected documents | Sandeep |  | Dept Admin (project owner) |  | 1. Select/deselect a couple of documents in the project (FileText/'Select' button). 2. Ask the Project Chat a question that only an unselected document could answer — confirm it's not used as a source. 3. Ask a question a selected document can answer. | Only selected documents are used as chat context; the assistant should decline or ignore unselected-document content.
T48 | G. Projects & Topics | [Bug-hunt] 'Clear Chat' button shown to non-owner admin — does it work? | Tanzeela |  | Super Admin, viewing a project owned by someone else | Open a project owned by Sandeep or Simran, where the 'Clear Chat' trash icon is visible to you (Super Admin/Dept Admin have this visible via a 'canManage' permission). | 1. Click Clear Chat and confirm. 2. Note the actual result. | Note whether it succeeds or fails — project chat clearing may be restricted to the literal owner server-side even though the button is shown to admins. Report the actual outcome (this specifically checks for a button that's visible but non-functional). | Bug-hunt
T49 | G. Projects & Topics | Project Timeline | Sandeep |  | Dept Admin |  | 1. Open the 'Timeline (N)' accordion in a project with tracked decisions. | Shows dated decision events with rationale and links back to source documents.
T50 | H. Org AI Assistant | Ask a question and watch it stream | Simran |  | Employee | Org has a valid OpenAI key configured. | 1. Start a New Conversation in org Chat. 2. Ask a question you know the answer to (based on uploaded docs). 3. Watch the answer stream token-by-token and check the confidence badge (high/med/low). | Answer streams in smoothly with a 'Thinking…' state, then shows a confidence badge.
T51 | H. Org AI Assistant | Citations — document and decision sources | Simran |  | Employee |  | 1. Ask a question that should cite a document. 2. Click a source/citation chip — confirm the modal shows filename/department/project and an 'Open Source Document' link. 3. If a 'Decision' (purple) citation appears, click it and confirm it shows the statement + rationale. | Both citation types open correctly-formatted modals; opening the source document works in a new tab.
T52 | H. Org AI Assistant | Rate an answer (thumbs up/down) | Simran |  | Employee |  | 1. On a completed AI answer, click thumbs-up. 2. Click it again to un-rate. 3. Click thumbs-down on another answer. | Rating toggles correctly and persists on reload.
T53 | H. Org AI Assistant | Conversation management — rename & delete | Simran |  | Employee |  | 1. Rename a conversation via the pencil icon (inline edit). 2. Delete a conversation via the trash icon. | Rename saves inline; delete removes it from the sidebar list immediately.
T54 | H. Org AI Assistant | Suggested experts panel | Simran |  | Employee |  | 1. Type a question (2+ characters) and watch for a 'suggested experts' / people-to-ask panel. | Panel populates with relevant people based on the question topic.
T55 | H. Org AI Assistant | Conversation privacy across users | Johurul | Simran | Two different users (pair with Simran) | Simran has at least one org-chat conversation. | 1. As Johurul (a different user), open org Chat and confirm you do NOT see Simran's conversations in your sidebar, and cannot load/rename/delete them directly. | Each user only ever sees, renames, deletes, and rates their own conversations.
T56 | H. Org AI Assistant | No-API-key friendly error message | Tanzeela |  | Super Admin | Temporarily remove the org's OpenAI key (Settings → API Key → clear & save). | 1. With no key configured, ask a question in org Chat. 2. Afterwards, re-add a valid key so other testers aren't blocked. | Shows a friendly message like 'This organization has no OpenAI API key configured. Ask a super admin to set one in Settings.' instead of a generic error/crash.
T57 | I. Needs Review Queue | Non-super-admin cannot access Needs Review | Johurul |  | Guest or Employee |  | 1. Navigate directly to the Needs Review URL for the org. | Redirected away to the Repository page (not a blank/error page).
T58 | I. Needs Review Queue | Filter the review queue | Tanzeela |  | Super Admin | Some documents pending review (manual + SharePoint-sourced if available). | 1. Filter by Source (Manual/SharePoint) and by Department, individually and combined. | Filters narrow the queue correctly.
T59 | I. Needs Review Queue | Accept a suggested document as-is | Tanzeela |  | Super Admin |  | 1. On a queued document, click Accept. | Document is confirmed/published with its suggested classification and disappears from the queue.
T60 | I. Needs Review Queue | Reassign a document to a different department / new project | Tanzeela |  | Super Admin |  | 1. Click Reassign on a queued document. 2. Pick a different department. 3. Check 'Assign to a new project under this department', name it, submit. | Reassign-only works; reassign-with-new-project creates the project and links the document.
T61 | I. Needs Review Queue | Resolve a duplicate flag from the queue | Tanzeela |  | Super Admin | A queued document flagged as a possible duplicate. | 1. Click Confirm on the duplicate banner for one document. 2. Click Dismiss on another. | Confirm/Dismiss both clear the duplicate banner appropriately.
T62 | J. SharePoint Integration | Non-super-admin cannot access the SharePoint integration page | Johurul |  | Guest |  | 1. Navigate directly to the SharePoint integration URL for the org. | Redirected to Settings (not a blank/error page).
T63 | J. SharePoint Integration | Connect SharePoint via OAuth | Tanzeela |  | Super Admin | Use the existing test tenant set up for SharePoint testing (mock org 'NGI', nextgenerationinnovation.onmicrosoft.com) rather than a real customer tenant. | 1. Settings → Integrations → SharePoint → Connect SharePoint. 2. Complete the Microsoft OAuth consent flow with the test tenant credentials. | OAuth completes and redirects back into the app's site-picker step. If it fails, the page shows a specific connectError banner, not a silent failure.
T64 | J. SharePoint Integration | Site picker — map sites to departments | Tanzeela |  | Super Admin | Just completed OAuth connect. | 1. On the site picker, map at least one SharePoint site to a department. 2. Try clicking Confirm with nothing mapped — should be blocked. 3. Map correctly and Confirm. | Confirm is disabled/blocked until at least one site→department mapping is chosen; valid confirm proceeds to the connected state.
T65 | J. SharePoint Integration | Manual sync + sync history | Tanzeela |  | Super Admin | SharePoint connected with at least one site mapped. | 1. Click 'Sync Now'. 2. Watch Sync History for a new run entry, and confirm it eventually shows completed/failed with a files-found count. | Sync run appears with correct status and counts; failures show a useful error message rather than nothing.
T66 | J. SharePoint Integration | Synced documents land in Needs Review | Tanzeela |  | Super Admin | A completed sync run with files found. | 1. Go to Needs Review, filter Source = SharePoint. 2. Confirm the newly synced files appear there for classification. | Synced files show up correctly tagged as SharePoint-sourced and can be Accepted/Reassigned like manual uploads.
T67 | J. SharePoint Integration | Disconnect SharePoint | Tanzeela |  | Super Admin |  | 1. Click Disconnect, confirm the dialog. | Integration returns to a disconnected state; a reconnect flow is still available afterward.
T68 | K. Billing & Subscription | Non-super-admin is blocked from Billing | Johurul |  | Dept Admin, Employee, or Guest |  | 1. Navigate directly to the Billing page URL. | Shows 'Only the org's super admin can manage billing' with a way back to the Dashboard — not a crash.
T69 | K. Billing & Subscription | View current plan and usage / tier comparison | Tanzeela |  | Super Admin |  | 1. Open Billing. 2. Review current plan, usage (storage), and other plan cards. 3. Confirm plans at or below your current tier show a disabled 'Not Available' / 'Current Plan' state rather than an active Upgrade button. | Current plan and usage are shown accurately; downgrade/same-tier options are correctly disabled.
T70 | K. Billing & Subscription | Upgrade plan via Stripe | Tanzeela |  | Super Admin |  | 1. Click Upgrade on a higher tier plan. | Redirects to Stripe Checkout/portal to complete the upgrade.
T71 | K. Billing & Subscription | Manage billing & payment via Stripe portal | Tanzeela |  | Super Admin |  | 1. Click 'Manage billing & payment'. | Redirects to the Stripe customer portal for payment method / invoice management.
T72 | L. Dashboard & Knowledge Health | Employee/Guest cannot reach the Dashboard | Johurul |  | Employee or Guest |  | 1. Navigate directly to the Dashboard URL for the org. | Redirected to the org home page — Dashboard is Super Admin/Dept Admin only.
T73 | L. Dashboard & Knowledge Health | Stat tiles + API-key nudge banner | Tanzeela |  | Super Admin |  | 1. Open Dashboard, click each stat tile (Documents/Members/Departments/Projects) and confirm it deep-links to the right page. 2. With no API key configured, confirm the 'Set up API key' banner appears; with a key configured, confirm it's gone. | All 4 tiles navigate correctly; the API-key banner only shows for Super Admin with no key configured.
T74 | L. Dashboard & Knowledge Health | Knowledge Health section | Tanzeela |  | Super Admin or Dept Admin | Enough Q&A/document activity to populate health data. | 1. Review the Answer Confidence tile (avg % + high/med/low distribution). 2. Click the Open Conflicts tile — review the modal listing conflicting document pairs, and click through to a document. 3. Review the Top Knowledge Gaps tile. | All three sub-sections render real data (or a sensible empty state) without errors; the conflicts modal links work.
T75 | L. Dashboard & Knowledge Health | Recently Created Projects & Documents feeds | Sandeep |  | Dept Admin |  | 1. Review the 'Recently Created Projects' and 'Recently Created Documents' lists. 2. Click into a couple of items. | Lists show the most recent items (max 5 each) and clicking navigates to the right project/document.
T76 | M. Audit Log & Security | Org chat audit log — filter + pagination | Tanzeela |  | Super Admin | Some chat activity has occurred, including at least one denied/unauthorized attempt if possible. | 1. Settings → Audit Log tab. 2. Filter by outcome: All / Answered / Denied. 3. Paginate with Previous/Next. | Log entries show question, user, timestamp, and cited docs; filters and pagination work correctly.
T77 | M. Audit Log & Security | Security events feed | Tanzeela |  | Super Admin | Some role grants and department create/rename/delete events have occurred (from earlier tests). | 1. Review the Security Events sub-section of the Audit Log tab. | Shows a read-only feed of role grants and department lifecycle events (create/rename/delete) matching what actually happened during testing.
T78 | N. Invite Acceptance | Accept an invite while signed out | Sandeep |  | Newly invited user, not yet signed in | Tanzeela has sent you an invite email/link (see Setup). | 1. Open the invite link in a private/incognito window (not signed in). 2. Confirm you're prompted to sign in, and that after signing in you land back on the invite page automatically. | Unauthenticated visitors see 'You need to sign in to accept this invitation' with a working sign-in redirect back to the invite.
T79 | N. Invite Acceptance | Accept an invite while signed in — role/departments applied correctly | Simran |  | Newly invited user, signed in |  | 1. Open your invite link while already signed in. 2. Confirm the displayed role/department(s) match what Tanzeela actually invited you as. 3. Click Accept. | Displayed role/department(s) are accurate; after accepting you land in the org with exactly that role and department access — verify by checking what you can/can't see.
T80 | N. Invite Acceptance | Decline invite, and expired/invalid token handling | Johurul |  | Newly invited user | Ask Tanzeela for a spare invite to decline, and reuse an already-accepted or manually expired invite link for the second part. | 1. Open an invite and click Decline — confirm no org membership is created (you're routed to Welcome Back). 2. Open an already-used or expired invite link. 3. Confirm you get an 'Invite Unavailable' message, not a crash. | Decline creates no membership. Invalid/expired tokens show a clear 'Invite Unavailable' state with a way back to your orgs.
T81 | O. Permission Boundary Sweep | Direct-URL access sweep for admin-only pages | Johurul |  | Guest (repeat as Employee if time allows) |  | 1. While signed in as Guest, try navigating directly (typing the URL) to: Dashboard, Settings, Needs Review, Billing, SharePoint Integration. 2. Note for each: blocked with redirect, or actually loads content it shouldn't. | Every admin-only page should redirect a Guest away cleanly. Report any URL that actually renders admin content for a Guest — that's a real bug, not just a UI nuisance. | Bug-hunt
T82 | O. Permission Boundary Sweep | Guest cannot invite others or see admin controls | Johurul |  | Guest |  | 1. As Guest, open whatever Settings/Members view is reachable. 2. Confirm there's no 'Invite Member' button and no way to change anyone's role. | Guest has view-only access with no path to invite or manage members.

## Tanzeela
Test ID | Section | Test Title | Pair With | Role / Persona Required | Preconditions | Steps | Expected Result | Tag | Status (Pass/Fail/Blocked) | Bug Description / Notes | Severity (Low/Med/High/Critical) | Date Tested
T6 | B. Org Onboarding (Super Admin) | Create a new organization |  | New user (becomes Super Admin) | Fresh account with no org membership yet. | 1. Sign up / sign in with a brand-new account. 2. You should land on the 'Create organization' onboarding screen — enter an org name and submit. | Organization is created and you're taken straight into the Billing step of onboarding. Your role in this org is Super Admin. |  | Pass | - | - | 2026-08-10
T7 | B. Org Onboarding (Super Admin) | Onboarding — subscribe to a plan |  | Super Admin, onboarding | Just created the org. | 1. On the Billing onboarding step, toggle Monthly/Yearly and review plan cards. 2. Subscribe to a plan. | Redirects to Stripe Checkout; after completing payment you land back in the app on the API Key onboarding step. |  | Pass | - | - | 2026-08-10
T8 | B. Org Onboarding (Super Admin) | Onboarding — OpenAI API key setup |  | Super Admin, onboarding | Subscription active. | 1. Enter an obviously invalid key and click 'Verify Key' — confirm it's rejected with an error. 2. Enter a real, valid OpenAI key and click 'Verify Key'. 3. Once verified, click 'Save & Continue'. | Invalid key is rejected with a clear message and 'Save & Continue' stays hidden until verified. Valid key saves and advances to the Celebrate screen. |  | Pass | - | - | 2026-08-10
T9 | B. Org Onboarding (Super Admin) | Celebrate screen is one-time only |  | Super Admin | Just finished the API key step. | 1. Confirm the celebration/completion screen appears and click 'Go to home page'. 2. Manually navigate back to the onboarding celebrate URL for the same org. | First visit shows the celebration and marks onboarding complete. Revisiting the URL afterward redirects straight to the org home instead of re-showing it. |  | Pass | - | - | 2026-08-10
T10 | B. Org Onboarding (Super Admin) | Welcome Back screen / org switching |  | User in one or more orgs | Belongs to at least one org. | 1. Sign in and observe the 'Welcome Back' screen. 2. If you belong to more than one org, switch between them. | Welcome Back lists your org(s) and lets you enter one; the app remembers your last-active org on next login. |  | Pass | - | - | 2026-08-10
T11 | C. Org Settings | Rename the organization |  | Super Admin |  | 1. Go to Settings → General tab. 2. Change the organization name and Save. | Name updates and is reflected across the app (sidebar/header). |  | Fail | The new organization name appears only after the screen is refreshed | Low | 2026-08-10
T12 | C. Org Settings | Invite members with each role (dept_admin / employee / guest) |  | Super Admin |  | 1. Settings → Members tab → Invite Member. 2. Choose role 'Department Admin' — confirm you CANNOT submit until you also pick at least one department. 3. Send invites for one dept_admin, one employee, and one guest (use real test emails for your 3 teammates). | Role dropdown only offers Department Admin / Employee / Guest (not Super Admin). Dept-admin invite is blocked until a department is chosen. Invited users receive an invite link/email. | Setup | Pass | - | - | 2026-08-10
T13 | C. Org Settings | Reassign a Department Admin's departments |  | Super Admin | At least one dept_admin exists (e.g. Sandeep) and 2+ departments exist. | 1. Settings → Members tab, find the dept_admin row, click 'Manage departments'. 2. Toggle which departments they administer, Save. | Checklist reflects current department assignments and saving updates them (verify by having that dept_admin test access to the added/removed department). |  | Pass | - | - | 16/08/2026
T14 | C. Org Settings | Department CRUD from Settings |  | Super Admin |  | 1. Settings → Departments tab → create a new department. 2. Rename it using the pencil icon. 3. Delete it using the trash icon — if a confirmation about existing content appears, confirm twice as prompted. | Create/rename/delete all work only for Super Admin (pencil/trash icons should not appear for dept_admin or employee viewing the same tab). Delete asks for confirmation, especially if the department has documents/projects. |  | Pass | - | - | 2026-08-10
T15 | C. Org Settings | OpenAI API key management |  | Super Admin |  | 1. Settings → API Key tab. 2. Replace the existing key with a new valid one, Save. 3. Clear the field and Save to remove the key entirely. | Key can be set, replaced, and removed. 'Configured' badge reflects current state. (Cross-check: after removing the key, org-level AI Chat should show the 'no API key configured' message — see Test on org chat.) |  | Pass | - | - | 2026-08-10
T16 | C. Org Settings | Integrations tab overview |  | Super Admin |  | 1. Settings → Integrations tab. | Shows SharePoint (and any other connectors) with connection status, site count, and last sync date; ' Manage' navigates to the connector's own page. |  | Fail | After clicking the connect share point button, this window popped up, Please note that the tester doesn't have any share point account https://drive.google.com/file/d/10ZNxeykQuzFQ7Mb6a_7AXhmPDgAovsXg/view?usp=sharing | Medium | 2026-08-12
T37 | F. Document Detail Page | [Bug-hunt] Admin viewing a colleague's document — do owner-only actions actually work? |  | Super Admin, viewing a document owned by someone else | Open a document uploaded by Sandeep or Simran (not you), while logged in as Super Admin. | 1. Try: Regenerate Summary, Ask a question in Chat, Clear Chat, Star, Rename, Delete. 2. For each, note whether it visibly works, silently does nothing, or shows an error. | Record actual behavior for each action — the buttons appear enabled/active regardless of ownership, so this is specifically checking whether that's misleading. Report anything that looks 'broken' (button clickable but nothing happens, no error shown) as a bug. | Bug-hunt
T48 | G. Projects & Topics | [Bug-hunt] 'Clear Chat' button shown to non-owner admin — does it work? |  | Super Admin, viewing a project owned by someone else | Open a project owned by Sandeep or Simran, where the 'Clear Chat' trash icon is visible to you (Super Admin/Dept Admin have this visible via a 'canManage' permission). | 1. Click Clear Chat and confirm. 2. Note the actual result. | Note whether it succeeds or fails — project chat clearing may be restricted to the literal owner server-side even though the button is shown to admins. Report the actual outcome (this specifically checks for a button that's visible but non-functional). | Bug-hunt | Pass | - | - | 2026-08-16
T56 | H. Org AI Assistant | No-API-key friendly error message |  | Super Admin | Temporarily remove the org's OpenAI key (Settings → API Key → clear & save). | 1. With no key configured, ask a question in org Chat. 2. Afterwards, re-add a valid key so other testers aren't blocked. | Shows a friendly message like 'This organization has no OpenAI API key configured. Ask a super admin to set one in Settings.' instead of a generic error/crash. |  | Pass | - | - | 2026-08-12
T58 | I. Needs Review Queue | Filter the review queue |  | Super Admin | Some documents pending review (manual + SharePoint-sourced if available). | 1. Filter by Source (Manual/SharePoint) and by Department, individually and combined. | Filters narrow the queue correctly.
T59 | I. Needs Review Queue | Accept a suggested document as-is |  | Super Admin |  | 1. On a queued document, click Accept. | Document is confirmed/published with its suggested classification and disappears from the queue.
T60 | I. Needs Review Queue | Reassign a document to a different department / new project |  | Super Admin |  | 1. Click Reassign on a queued document. 2. Pick a different department. 3. Check 'Assign to a new project under this department', name it, submit. | Reassign-only works; reassign-with-new-project creates the project and links the document.
T61 | I. Needs Review Queue | Resolve a duplicate flag from the queue |  | Super Admin | A queued document flagged as a possible duplicate. | 1. Click Confirm on the duplicate banner for one document. 2. Click Dismiss on another. | Confirm/Dismiss both clear the duplicate banner appropriately. |  | Pass | - | - | 2026-08-16
T63 | J. SharePoint Integration | Connect SharePoint via OAuth |  | Super Admin | Use the existing test tenant set up for SharePoint testing (mock org 'NGI', nextgenerationinnovation.onmicrosoft.com) rather than a real customer tenant. | 1. Settings → Integrations → SharePoint → Connect SharePoint. 2. Complete the Microsoft OAuth consent flow with the test tenant credentials. | OAuth completes and redirects back into the app's site-picker step. If it fails, the page shows a specific connectError banner, not a silent failure. |  | Blocked | SharePoint connection itself isn't working | Medium | 2026-08-16
T64 | J. SharePoint Integration | Site picker — map sites to departments |  | Super Admin | Just completed OAuth connect. | 1. On the site picker, map at least one SharePoint site to a department. 2. Try clicking Confirm with nothing mapped — should be blocked. 3. Map correctly and Confirm. | Confirm is disabled/blocked until at least one site→department mapping is chosen; valid confirm proceeds to the connected state. |  | Blocked | Requires successful OAuth | Medium | 2026-08-16
T65 | J. SharePoint Integration | Manual sync + sync history |  | Super Admin | SharePoint connected with at least one site mapped. | 1. Click 'Sync Now'. 2. Watch Sync History for a new run entry, and confirm it eventually shows completed/failed with a files-found count. | Sync run appears with correct status and counts; failures show a useful error message rather than nothing. |  | Blocked | Requires connected SharePoint + mapped site | Medium | 2026-08-16
T66 | J. SharePoint Integration | Synced documents land in Needs Review |  | Super Admin | A completed sync run with files found. | 1. Go to Needs Review, filter Source = SharePoint. 2. Confirm the newly synced files appear there for classification. | Synced files show up correctly tagged as SharePoint-sourced and can be Accepted/Reassigned like manual uploads. |  | Blocked | Requires successful sync with files | Medium | 2026-08-16
T67 | J. SharePoint Integration | Disconnect SharePoint |  | Super Admin |  | 1. Click Disconnect, confirm the dialog. | Integration returns to a disconnected state; a reconnect flow is still available afterward. |  | Blocked | Ideally requires an established connection | Medium | 2026-08-16
T69 | K. Billing & Subscription | View current plan and usage / tier comparison |  | Super Admin |  | 1. Open Billing. 2. Review current plan, usage (storage), and other plan cards. 3. Confirm plans at or below your current tier show a disabled 'Not Available' / 'Current Plan' state rather than an active Upgrade button. | Current plan and usage are shown accurately; downgrade/same-tier options are correctly disabled. |  | Pass | - | - | 2026-08-13
T70 | K. Billing & Subscription | Upgrade plan via Stripe |  | Super Admin |  | 1. Click Upgrade on a higher tier plan. | Redirects to Stripe Checkout/portal to complete the upgrade. |  | Pass | - | - | 2026-08-13
T71 | K. Billing & Subscription | Manage billing & payment via Stripe portal |  | Super Admin |  | 1. Click 'Manage billing & payment'. | Redirects to the Stripe customer portal for payment method / invoice management. |  | Pass | - | - | 2026-08-13
T73 | L. Dashboard & Knowledge Health | Stat tiles + API-key nudge banner |  | Super Admin |  | 1. Open Dashboard, click each stat tile (Documents/Members/Departments/Projects) and confirm it deep-links to the right page. 2. With no API key configured, confirm the 'Set up API key' banner appears; with a key configured, confirm it's gone. | All 4 tiles navigate correctly; the API-key banner only shows for Super Admin with no key configured. |  | Pass | - | - | 2026-08-13
T74 | L. Dashboard & Knowledge Health | Knowledge Health section |  | Super Admin or Dept Admin | Enough Q&A/document activity to populate health data. | 1. Review the Answer Confidence tile (avg % + high/med/low distribution). 2. Click the Open Conflicts tile — review the modal listing conflicting document pairs, and click through to a document. 3. Review the Top Knowledge Gaps tile. | All three sub-sections render real data (or a sensible empty state) without errors; the conflicts modal links work. |  | Pass | - | - | 2026-08-16
T76 | M. Audit Log & Security | Org chat audit log — filter + pagination |  | Super Admin | Some chat activity has occurred, including at least one denied/unauthorized attempt if possible. | 1. Settings → Audit Log tab. 2. Filter by outcome: All / Answered / Denied. 3. Paginate with Previous/Next. | Log entries show question, user, timestamp, and cited docs; filters and pagination work correctly. |  | Pass | - | - | 2026-08-16
T77 | M. Audit Log & Security | Security events feed |  | Super Admin | Some role grants and department create/rename/delete events have occurred (from earlier tests). | 1. Review the Security Events sub-section of the Audit Log tab. | Shows a read-only feed of role grants and department lifecycle events (create/rename/delete) matching what actually happened during testing. |  | Pass | - | - | 2026-08-16
ADDITIONAL TESTS
Test ID | Section | Test Title | Pair With | Role / Persona Required | Preconditions | Steps | Expected Result | Tag | Status (Pass/Fail/Blocked) | Bug Description / Notes | Severity (Low/Med/High/Critical) | Date Tested
T81 | E. Central Repository / Projects | Department Admin document visible in Repository but not inside Project |  | Super Admin + Department Admin | Department Admin has uploaded a document and it is visible in the Knowledge Repository. | 1. Open Knowledge Repository and locate the document uploaded by the Department Admin. 2. Open the relevant project. 3. Check whether the same document is listed inside the project. | A document associated with a project should be visible inside that project to users with access. | Bug | Fail | The document uploaded by the Department Admin is visible in the Knowledge Repository and its category is visible, but the actual document is not visible inside the relevant project. | High | 2026-08-17
T82 | E. Central Repository / Duplicate Detection | Duplicate document uploaded by Department Admin is not flagged |  | Department Admin | The same document already exists in the organization/repository. | 1. Upload the same document again using the Department Admin account. 2. Check whether the system identifies it as a duplicate. 3. Check Needs Review and Repository. | The system should identify the duplicate and handle it through the duplicate-review workflow. | Bug | Fail | The same document was uploaded from the Department Admin account, but no duplicate flag appeared. The document was visible in the Knowledge Repository. | High | 2026-08-17
T83 | G. Projects & Topics | Project Chat not functioning |  | Super Admin + Department Admin | A project contains documents accessible to the tester. | 1. Open Project Chat as Super Admin. 2. Ask a question based on project documents. 3. Repeat using Department Admin. 4. Repeat across tested departments/projects. | Project Chat should return an answer using the project's document context. | Bug | Fail | Project Chat is not working properly across the tested departments. The issue reproduces for both Super Admin and Department Admin. Document Chat works with the same setup. | High | 2026-08-17
T84 | F. Document Detail / Repository | Excel/XLSX document does not open |  | Super Admin / Department Admin | An XLSX document has been uploaded. | 1. Open the XLSX document from Repository/project. 2. Attempt to open or preview the file. | The Excel file should open and display its sheet/column information without errors. | Bug | Fail | Excel files are currently not opening properly, blocking XLSX preview validation. | High | 2026-08-17
T85 | I. Needs Review Queue | Reassign action availability |  | Super Admin | A document is present in Needs Review and requires reassignment. | 1. Open Needs Review. 2. Select a queued document. 3. Check available actions for Reassign. 4. If available, reassign it to another department/project. | A queued document should expose the Reassign action as specified in T60. | Additional Test | Blocked | No documents are currently appearing in Needs Review for the tested Manual + Marketing filter, so the Reassign action cannot yet be verified. T60 explicitly expects a Reassign action on a queued document. | Medium | 2026-08-17
T86 | E. Central Repository / Project Access | Project document list does not match Repository visibility |  | Super Admin + Department Admin | Documents are present in Repository and assigned to the department/project. | 1. Compare documents visible in Repository with documents listed inside the corresponding project. 2. Identify documents visible in Repository but absent from the project. | Project document listings should be consistent with the Repository/project association and permissions. | Bug | Fail | There is a mismatch between Repository visibility and Project visibility: documents can be found through the Repository/category but are absent from the corresponding project view. | High | 2026-08-17

## Sandeep
Test ID | Section | Test Title | Pair With | Role / Persona Required | Preconditions | Steps | Expected Result | Tag | Status (Pass/Fail/Blocked) | Bug Description / Notes | Severity (Low/Med/High/Critical) | Date Tested
T17 | D. Department Management | Open a department and confirm its 4 tabs |  | Dept Admin (admin of this department) |  | 1. Open a department you administer. 2. Confirm Documents / Projects / Members / Timeline tabs all load. | All 4 tabs render without errors. |  | Pass | Documents, Projects, Members, and Timeline tabs loaded without errors.
T18 | D. Department Management | Upload documents scoped to a department |  | Dept Admin |  | 1. Documents tab → Upload Document. 2. Drag-and-drop (or browse) 2-3 files of mixed types (.pdf/.docx/.xlsx/.csv/.txt), try exceeding 10 files or an unsupported type to confirm it's rejected. 3. Pick a required Document Type category, submit. | Only accepted file types/count are allowed; clear error otherwise. Upload succeeds and documents appear (possibly first in Needs Review, depending on classification). |  | Pass | Accepted mixed document types uploaded successfully; invalid file type/count validation behaved as expected.
T19 | D. Department Management | Filter documents in the department view |  | Dept Admin | Department has several documents with different categories/types/lifecycle states. | 1. Apply Category, File Type, Lifecycle, and Date-range filters one at a time and in combination. | Each filter narrows results correctly; clearing filters restores the full list. |  | Pass | Category, file type, lifecycle, and date filters narrowed results correctly; clearing filters restored the full list.
T20 | D. Department Management | Lifecycle transitions — allowed vs. blocked for Dept Admin |  | Dept Admin | Have one document you administer, and (if possible) one document in a department you do NOT administer. | 1. On a document in a department you ADMINISTER: change draft → published, then published → archived. Confirm both succeed. 2. Try published → retired or archived → anything: confirm the option is not offered / is rejected (Super Admin only). 3. If you have access to a document in a department you do NOT administer, try any lifecycle change there too. | Dept Admin can publish and archive only within departments they administer; retiring/un-archiving/reverting to draft is Super-Admin-only; attempting a transition in a department you don't administer is rejected. |  | Pass | Dept Admin lifecycle transitions worked within administered departments; restricted transitions remained unavailable.
T21 | D. Department Management | Classification, duplicate, and lifecycle-suggestion banners |  | Dept Admin | A document flagged 'needs review' with a suggested category/department, and/or a possible-duplicate flag. | 1. Open the classification review panel on a flagged document, adjust the suggested category/department, accept it. 2. On a document with a duplicate-signal banner, click Confirm, then on another try Dismiss. 3. On a document with a lifecycle-suggestion banner, dismiss it. | Accepting classification updates the doc's category/department. Confirming a duplicate flag marks it; dismissing clears the banner. Lifecycle-suggestion banner dismiss removes it without changing lifecycle. |  | Pass | Classification review, duplicate Confirm/Dismiss, and lifecycle-suggestion dismissal behaved as expected.
T22 | D. Department Management | Project CRUD within a department |  | Dept Admin |  | 1. Projects tab → New Project (name + description). 2. Hover a project card → Edit (pencil) → change name/description, Save. 3. Hover → Delete (trash) → confirm. | Create/edit/delete all succeed for the department's admin. |  | Pass | Project create, edit, and delete actions succeeded within the administered department.
T23 | D. Department Management | Department member management + bulk add-members modal |  | Dept Admin |  | 1. Members tab → Add member by email with role Member or Admin. 2. Remove a member (trash/X icon), confirm the prompt. 3. Create a brand-new department as Super Admin (or watch Tanzeela do it) and confirm the 'Add Members' bulk modal auto-opens right after creation, letting you multi-select org members with per-row role. | Add/remove work and reflect immediately in the list. New-department bulk-add modal appears automatically once, with working multi-select + per-row role. |  | Pass | Department member add/remove actions and bulk member selection behaved as expected.
T24 | D. Department Management | Department Timeline tab |  | Dept Admin | Department has some documents with extracted decisions. | 1. Open the Timeline tab. | Read-only, dated list of decision events with rationale and a link back to the source document. |  | Pass | Department Timeline displayed dated decision events with rationale and source-document links.
T38 | F. Document Detail Page | [Bug-hunt] Dept Admin viewing a colleague's document in their own department |  | Dept Admin, viewing a document owned by someone else in a department they administer | Open a teammate's document in a department you administer. | 1. Try the same set of actions: Regenerate Summary, Ask, Clear Chat, Star, Rename, Delete. 2. Note pass/fail/silent-fail for each. | Same as above — document and report actual behavior, especially anything that looks clickable but does nothing. | Bug-hunt | Fail | Regenerate Summary permission mismatch for a Dept Admin viewing another user's document: the UI can expose Regenerate, but the regenerate API requires literal document ownership. | Medium
T39 | G. Projects & Topics | Project CRUD from the Projects list |  | Dept Admin |  | 1. Projects page → search/filter by name. 2. Create a new project (choose department). 3. Edit an existing project's name/description. 4. Delete a project you created, confirm the dialog. | Search filters client-side instantly; create/edit/delete all succeed. |  | Pass | Project search, create, edit, and delete actions worked correctly from the Projects list.
T41 | G. Projects & Topics | Upload documents into a project |  | Dept Admin |  | 1. Open a project → Upload. 2. Upload a file, set category and Private/Public visibility. 3. Re-upload a file with the exact same name to confirm duplicate-filename detection. | Upload succeeds with required fields; re-uploading the same filename surfaces a clear duplicate-filename error inline. |  | Pass | Project document upload worked with category/visibility selection and duplicate-filename validation.
T42 | G. Projects & Topics | Topic clustering view |  | Dept Admin | A project with several documents, some auto-clustered into topics. | 1. Open a project and review the Topic groups plus the always-present 'Unassigned' group. 2. Toggle grid/list view and try the search box and Starred/Unselected filter chips. | Documents are grouped sensibly by topic; view toggle, search, and filter chips all work. |  | Pass | Topic groups, Unassigned section, grid/list toggle, search, and filter chips worked correctly.
T43 | G. Projects & Topics | Drag-and-drop a document between topics |  | Dept Admin (or document owner) |  | 1. Drag a document row by its grip handle onto a different Topic header. 2. Drag a document onto 'Unassigned' to unassign it. | Document moves to the target topic (or becomes unassigned) and the UI updates without a full reload. |  | Pass | Documents moved between topics and to Unassigned successfully without requiring a full reload.
T44 | G. Projects & Topics | Rename and delete a topic |  | Dept Admin |  | 1. Click the pencil icon on a topic header, rename it inline. 2. Click the trash icon on a topic header, confirm the browser confirm dialog. | Rename and delete both succeed. |  | Pass | Topic rename and delete actions succeeded for the Dept Admin.
T46 | G. Projects & Topics | Auto-organize / Recluster — as project owner vs. non-owner admin | Tanzeela | Dept Admin | A project you personally created/own, with unassigned documents. | 1. As the project owner, click 'Auto-organize' (Sparkles icon) on the Unassigned group and confirm it clusters documents into topics. 2. Now have Tanzeela (Super Admin, NOT the project owner) open the same project and try 'Auto-organize' too. | Works for the owner. For Tanzeela: note whether it works, fails silently, or shows an error — recluster may be restricted to the literal project owner even for Super Admin. | Bug-hunt | Fail | Recluster/Auto-organize is restricted to the literal project owner, so a non-owner Super Admin cannot recluster the project. | Medium
T47 | G. Projects & Topics | Project Chat — ask AI, restricted to selected documents |  | Dept Admin (project owner) |  | 1. Select/deselect a couple of documents in the project (FileText/'Select' button). 2. Ask the Project Chat a question that only an unselected document could answer — confirm it's not used as a source. 3. Ask a question a selected document can answer. | Only selected documents are used as chat context; the assistant should decline or ignore unselected-document content. |  | Pass | Project Chat used selected documents as context and did not rely on unselected documents.
T49 | G. Projects & Topics | Project Timeline |  | Dept Admin |  | 1. Open the 'Timeline (N)' accordion in a project with tracked decisions. | Shows dated decision events with rationale and links back to source documents. |  | Pass | Project Timeline displayed dated decisions, rationale, and source-document links correctly.
T75 | L. Dashboard & Knowledge Health | Recently Created Projects & Documents feeds |  | Dept Admin |  | 1. Review the 'Recently Created Projects' and 'Recently Created Documents' lists. 2. Click into a couple of items. | Lists show the most recent items (max 5 each) and clicking navigates to the right project/document. |  | Pass | Recent Projects and Documents feeds showed recent items and navigated to the correct records.
T78 | N. Invite Acceptance | Accept an invite while signed out |  | Newly invited user, not yet signed in | Tanzeela has sent you an invite email/link (see Setup). | 1. Open the invite link in a private/incognito window (not signed in). 2. Confirm you're prompted to sign in, and that after signing in you land back on the invite page automatically. | Unauthenticated visitors see 'You need to sign in to accept this invitation' with a working sign-in redirect back to the invite. |  | Pass | Signed-out invite flow prompted sign-in and returned to the invitation flow correctly.

## Simran
Test ID | Section | Test Title | Pair With | Role / Persona Required | Preconditions | Steps | Expected Result | Tag | Status (Pass/Fail/Blocked) | Bug Description / Notes | Severity (Low/Med/High/Critical) | Date Tested
T25 | E. Central Repository | Browse and filter the repository |  | Employee |  | 1. Open Repository. Apply Department, Category, File Type, Lifecycle, and Date filters, individually and combined. 2. Try pagination (Previous/Next). | Filters and pagination work; result count updates correctly; empty-filter combos show a clean empty state. |  | Pass | Repository filters and pagination working.
T26 | E. Central Repository | Upload + Open/Preview/Download from Repository |  | Employee |  | 1. Upload Document from the Repository page (choose a department, or 'Org-wide document'). 2. On an existing PDF, use Preview (should open inline) and Download. 3. On any document, use 'Open' (new tab) and 'View Details' (goes to the document page). | Upload succeeds; preview/download/open/view-details all work for accessible documents. |  | Pass | Upload, preview, download, open, and view details working.
T28 | E. Central Repository | Employee cannot change document lifecycle |  | Employee |  | 1. On any repository document card, look for a 'Change status…' lifecycle control. | No lifecycle-change control is available to a plain employee (dept_admin/super_admin only). |  | Pass | Employee cannot change document lifecycle.
T29 | F. Document Detail Page | Preview rendering across file types |  | Employee (owner or with access) | Have access to at least one PDF, DOCX, XLSX/CSV, and TXT document. | 1. Open each file type's document page and confirm the preview renders (PDF viewer w/ pages, DOCX text, spreadsheet with sheet/column breakdown, plain text). | Each format renders without errors or a broken viewer. |  | Pass | File previews render correctly.
T30 | F. Document Detail Page | Chat with a document you own |  | Employee (document owner) | Own at least one uploaded document. | 1. Open the Chat tab, ask a question about the document's content. 2. While it's answering, click the cancel/stop icon. 3. Ask again, let it finish, then use Copy / Print / Expand on the message. 4. Use the trash icon to Clear Chat, confirm the dialog. | Answer is relevant and (where applicable) cites sources. Cancel stops the in-flight response. Copy/print/expand controls work. Clear Chat empties the conversation after confirming. |  | Pass | Document chat functions correctly.
T31 | F. Document Detail Page | Summary tab — generate, regenerate, copy, print |  | Employee (document owner) |  | 1. Open Summary tab on an owned document. 2. Click Regenerate Summary (or Generate if none exists), wait for completion. 3. Copy the summary text and Print it. | Summary (re)generates successfully, button disables while processing, copy/print both work. |  | Pass | Summary generation, regenerate, copy, and print working.
T32 | F. Document Detail Page | Pagewise Summary reading guide |  | Employee (document owner) | A multi-page document. | 1. Open the Pagewise Summary tab and page/scroll through the document. 2. Expand/collapse a couple of page cards. | Key points and reflection questions generate per page as you progress; progress indicator advances; expand/collapse works. |  | Pass | Pagewise summary and progress tracking working.
T33 | F. Document Detail Page | Fullscreen viewer with zoom |  | Employee |  | 1. Click Fullscreen on a PDF/TXT/DOCX document. 2. Zoom in, zoom out, and reset. | Fullscreen modal opens correctly and zoom controls behave as expected. |  | Pass | Fullscreen viewer and zoom controls working.
T34 | F. Document Detail Page | Star a document and filter by it |  | Employee (document owner) |  | 1. Star one of your own documents. 2. Go to its Project page (or wherever a Starred filter exists) and confirm it's included. | Starring persists and the Starred filter correctly includes it. |  | Pass | Starred documents persist and filter correctly.
T35 | F. Document Detail Page | Rename and delete your own document |  | Employee (document owner) | Use a disposable test upload, not a document others depend on. | 1. Rename the document. 2. Delete it and confirm the confirmation dialog appears before it's removed. | Rename updates the filename everywhere it's shown. Delete requires confirmation and actually removes it. |  | Pass | Rename and delete own document working with confirmation.
T36 | F. Document Detail Page | Suggested project link — confirm/dismiss |  | Employee (document owner or admin) | A document with a suggested project link. | 1. Click Confirm on a suggested project link. 2. On another, click Dismiss. | Confirm attaches the document to that project; Dismiss removes the suggestion without linking. |  | Pass | Suggested project link Confirm/Dismiss working.
T40 | G. Projects & Topics | [Bug-hunt] Can an Employee or Guest create/edit/delete a project via the Projects list? |  | Employee | The Projects list page shows New Project / Edit / Delete controls to everyone who can reach it, with no visible role restriction in the UI. | 1. As Employee, try creating a new project. 2. Try editing and deleting a project you do NOT own (created by someone else). | Note whether this succeeds or is blocked. This is specifically testing whether the lack of a visible restriction means there's also no restriction on the server — report actual outcome either way. | Bug-hunt | Pass | Employee cannot edit/delete projects owned by others; server-side protection exists.
T45 | G. Projects & Topics | [Bug-hunt] Can any org member rename/delete a topic in someone else's project? |  | Employee, not part of the project's department | Find a project in a department you are NOT a member of. | 1. Try renaming a topic in that project. 2. Try deleting a topic in that project. | Note whether this is blocked or allowed — topic rename/delete may only require being *some* org member rather than being scoped to that project/department. Report the actual outcome. | Bug-hunt | Fail | Employee outside the department may be able to rename/delete topics in another department's project due to insufficient department-level authorization checks. | High
T50 | H. Org AI Assistant | Ask a question and watch it stream |  | Employee | Org has a valid OpenAI key configured. | 1. Start a New Conversation in org Chat. 2. Ask a question you know the answer to (based on uploaded docs). 3. Watch the answer stream token-by-token and check the confidence badge (high/med/low). | Answer streams in smoothly with a 'Thinking…' state, then shows a confidence badge. |  | Pass | AI Assistant streams responses correctly.
T51 | H. Org AI Assistant | Citations — document and decision sources |  | Employee |  | 1. Ask a question that should cite a document. 2. Click a source/citation chip — confirm the modal shows filename/department/project and an 'Open Source Document' link. 3. If a 'Decision' (purple) citation appears, click it and confirm it shows the statement + rationale. | Both citation types open correctly-formatted modals; opening the source document works in a new tab. |  | Pass | Citation modals and source links working.
T52 | H. Org AI Assistant | Rate an answer (thumbs up/down) |  | Employee |  | 1. On a completed AI answer, click thumbs-up. 2. Click it again to un-rate. 3. Click thumbs-down on another answer. | Rating toggles correctly and persists on reload. |  | Pass | Thumbs up/down rating persists correctly.
T53 | H. Org AI Assistant | Conversation management — rename & delete |  | Employee |  | 1. Rename a conversation via the pencil icon (inline edit). 2. Delete a conversation via the trash icon. | Rename saves inline; delete removes it from the sidebar list immediately. |  | Pass | Conversation rename and delete working.
T54 | H. Org AI Assistant | Suggested experts panel |  | Employee |  | 1. Type a question (2+ characters) and watch for a 'suggested experts' / people-to-ask panel. | Panel populates with relevant people based on the question topic. |  | Pass | Suggested Experts panel appears and populates.
T79 | N. Invite Acceptance | Accept an invite while signed in — role/departments applied correctly |  | Newly invited user, signed in |  | 1. Open your invite link while already signed in. 2. Confirm the displayed role/department(s) match what Tanzeela actually invited you as. 3. Click Accept. | Displayed role/department(s) are accurate; after accepting you land in the org with exactly that role and department access — verify by checking what you can/can't see. |  | Fail | Employee invite acceptance does not consistently apply invited department assignments after joining the organization. | High

## Johurul
Test ID | Section | Test Title | Pair With | Role / Persona Required | Preconditions | Steps | Expected Result | Tag | Status (Pass/Fail/Blocked) | Bug Description / Notes | Severity (Low/Med/High/Critical) | Date Tested
T1 | A. Authentication & Account | Sign up with a new email |  | New user | Use an email not already registered. | 1. Go to the Sign Up page. 2. Enter email + password, and try submitting WITHOUT checking the Terms & Conditions box (should be blocked). 3. Check the Terms & Conditions box and submit. | Blocked with a clear message when T&Cs unchecked. On valid submit, you're routed to the Verify OTP screen. |  | Pass | Note: styling the emails for otps amd other notifications.
T2 | A. Authentication & Account | Verify OTP + resend cooldown |  | New user | Just completed sign up. | 1. On the Verify OTP screen, enter an incorrect 6-digit code and submit. 2. Click 'Resend OTP' and confirm it goes into a ~30s cooldown (disabled/counting down). 3. Check email/inbox for the real code, enter it, submit. | Wrong code shows an inline error. Resend is rate-limited. Correct code verifies the account and routes to Sign In. |  | Pass
T3 | A. Authentication & Account | Sign in (valid + invalid credentials) |  | Any registered user | Account already verified. | 1. Try signing in with a wrong password — confirm an inline error appears, not a crash. 2. Sign in with correct credentials. | Wrong password is rejected gracefully. Correct login lands on Welcome Back / org home. |  | Pass | Note: Add invalide email or password in stead of just "Invalid email"
T4 | A. Authentication & Account | Forgot password → reset password flow |  | Any registered user |  | 1. From Sign In, click 'Forgot password?' and submit your email. 2. Note the message is generic either way (doesn't reveal whether the email exists). 3. On the Reset Password screen, enter the OTP from email + a new password + confirm password (try mismatched confirm first to check validation). 4. Submit with matching passwords. | Generic 'if this email exists...' message shown. Mismatched confirm is blocked client-side. Valid reset redirects to Sign In, and you can log in with the new password. |  | Pass | Note: Polish the reset password page. Add show and hide password. And Aligne both password field.
T5 | A. Authentication & Account | Change password while logged in + sign out |  | Any logged-in user |  | 1. Go to Settings → Change Password. 2. Change your password (enter current + new). 3. Sign out. 4. Sign back in with the NEW password to confirm it actually took effect. | Password change succeeds and old password no longer works; new password does. Sign out clears the session and returns you to Sign In. |  | Pass
T27 | E. Central Repository | Guest role — read-only repository access |  | Guest |  | 1. Open Repository as a Guest. 2. Confirm there is NO 'Upload Document' button. 3. Confirm you can still browse/open/download documents you have access to. | Guest cannot upload but retains read access to documents shared with them. |  | Pass | Note: I can see the documents but cant download or open, i see this error "This document could not be found, or you don't have access to it." If i try to download.
T55 | H. Org AI Assistant | Conversation privacy across users | Simran | Two different users (pair with Simran) | Simran has at least one org-chat conversation. | 1. As Johurul (a different user), open org Chat and confirm you do NOT see Simran's conversations in your sidebar, and cannot load/rename/delete them directly. | Each user only ever sees, renames, deletes, and rates their own conversations. |  | Pass
T57 | I. Needs Review Queue | Non-super-admin cannot access Needs Review |  | Guest or Employee |  | 1. Navigate directly to the Needs Review URL for the org. | Redirected away to the Repository page (not a blank/error page). |  | Pass
T62 | J. SharePoint Integration | Non-super-admin cannot access the SharePoint integration page |  | Guest |  | 1. Navigate directly to the SharePoint integration URL for the org. | Redirected to Settings (not a blank/error page). |  | Pass
T68 | K. Billing & Subscription | Non-super-admin is blocked from Billing |  | Dept Admin, Employee, or Guest |  | 1. Navigate directly to the Billing page URL. | Shows 'Only the org's super admin can manage billing' with a way back to the Dashboard — not a crash. |  | Pass | Note: Biling page needs work. especially to upgrade from monthly to yearly billing.
T72 | L. Dashboard & Knowledge Health | Employee/Guest cannot reach the Dashboard |  | Employee or Guest |  | 1. Navigate directly to the Dashboard URL for the org. | Redirected to the org home page — Dashboard is Super Admin/Dept Admin only. |  | Pass
T80 | N. Invite Acceptance | Decline invite, and expired/invalid token handling |  | Newly invited user | Ask Tanzeela for a spare invite to decline, and reuse an already-accepted or manually expired invite link for the second part. | 1. Open an invite and click Decline — confirm no org membership is created (you're routed to Welcome Back). 2. Open an already-used or expired invite link. 3. Confirm you get an 'Invite Unavailable' message, not a crash. | Decline creates no membership. Invalid/expired tokens show a clear 'Invite Unavailable' state with a way back to your orgs. |  | Partial | Bug: I opened the invite, clicked decline, no org was created. But when i opened the invite again the same option "Decline" and "Accept" appeared, the Invite did not expire. Also the email itself only shows the accept invite button and the takes to the actual invite page to accept or decline. It should say open Invite or somthing.
T81 | O. Permission Boundary Sweep | Direct-URL access sweep for admin-only pages |  | Guest |  | 1. While signed in as Guest, try navigating directly (typing the URL) to: Dashboard, Settings, Needs Review, Billing, SharePoint Integration. 2. Note for each: blocked with redirect, or actually loads content it shouldn't. | Every admin-only page should redirect a Guest away cleanly. Report any URL that actually renders admin content for a Guest — that's a real bug, not just a UI nuisance. | Bug-hunt | Pass
T82 | O. Permission Boundary Sweep | Guest cannot invite others or see admin controls |  | Guest |  | 1. As Guest, open whatever Settings/Members view is reachable. 2. Confirm there's no 'Invite Member' button and no way to change anyone's role. | Guest has view-only access with no path to invite or manage members. |  | Pass
Additional notes/bugs
| 1 | Bug: If the user is invited in an organization, and he or she has othe orgs. But if the current active orh is disabled or open ai key is missing then there is no way to switch to other orgs. it just shows that "XYZ Organization is locked" and "This organization hasn't configured an OpenAI API key yet. Contact an admin to restore access."
| 2 | Note: Right now super admin cannot edit any role
| 3 | Adding sharepoint app secrets and ids in the deployment env variables.